## Slide 1
TG3 Project Plan + Establishment Nordic Energy Data Quality Improvement – Phase 1
Author: NordicTech Solutions AB – S&BS Team
Status Report Date: 28 Nov 2025

## Slide 2: TG3 Project Plan + Establishment
Project Information:
Revision History:
Appendices:
Appendix 1: Meter Data Overview
Appendix 2: Data Cleaning Rules
Nordic Energy Data Quality Improvement – Phase 1
Novision Criteria:
<Mark Novision Criteria by changing to Checkmark Bullets>
Project ID | PRJ-NE-DQP-001 / CAT4-E-0785
Project Portfolio Owner | Emma Lindström
Project Sponsor | Jonas Hallberg
Project Manager | Maria Svensson +46 70 123 45 67 maria.svensson@nordictechsolutions.com
SAP code | Not applicable
Project Period | 1 Nov 2025 – 28 Nov 2025
Revision | Description of Change | Resp. | Effective Date
1.0 | First version | T. Carbin | 2025-11-01 (project start / first approved plan)
1.1 | Dummy data added to project plan sections | M. Svensson | 2025-11-08 (one week later, still early in the period)
 | Criteria | Comment
 | Strategic focus area compliance checked | Aligns with CO₂ reduction target
 | KPIs & Benefit realization detailed | KPIs created in scope section
 | Business Case detailed | Simple internal-cost model
 | Purpose, goals & deliverables detailed | Clear 3-task pilot scope
 | Scope/WBS & delimitations detailed | WBS provided in section 3
 | Requirements detailed | Minimal; access to meter files
 | Consequences, Dependencies, Risks & Handover detailed | Included in dedicated slide
 | Budget detailed and secured | €10,000 internal budget
 | Tender evaluation and final partner(s) selected | Not applicable
 | Solution implementation plan detailed | Timeline prepared
 | Partner contract & SLAs final commitment detailed | Not applicable
 | Organization allocated and approved | Small project team assigned
 | Communication Plan detailed | Weekly email updates
 | Support after Go-live detailed | Maintained by Energy Team
 | Lessons Learned documented | Will be added at TG4
Current revision: 1.1
Status Report Date: 28 Nov 2025

## Slide 3: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Project Description and Background:
The project aims to improve the quality of electricity meter data for three pilot buildings within the Nordic region. Currently, the data is stored in separate files with inconsistent formats, missing days, and manual corrections. This pilot project focuses on cleaning and standardizing the data to prepare for future reporting and analytics.
Purpose and Benefit Realization:
The purpose is to establish reliable and consistent energy consumption data. This improves reporting accuracy and supports the company’s CO₂ reduction and energy-efficiency goals.
Benefits:
Higher data accuracy
Faster monthly reporting
Foundation for future automation and dashboards
KPIs:
95% clean and validated data
One combined dataset for all 3 buildings
Monthly usage summary delivered
Nordic Energy Data Quality Improvement – Phase 1
Goals and Deliverables:
Goals:
Create a clean, unified dataset for 3 buildings
Enable simple monthly reporting
Ensure data reliability
Deliverables:
Cleaned dataset
Data validation summary
One monthly energy usage report
Resource or Expertise needs:
Project Manager – coordination and communication
Data Analyst – data cleaning and validation
IT Technician – access to meter data and source files
Expertise required: Basic data analysis, Excel file handling, and understanding of meter data structure.
Status Report Date: 28 Nov 2025

## Slide 4: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Business Impact, Cost, Benefits and ROI:
This pilot provides reliable energy data that supports sustainability reporting, cost efficiency, and CO₂ reduction strategy.
Cost: Approx. 75,000 SEK internal labor only.
Benefits:
More reliable monthly energy reporting
Reduced manual correction effort (approx. 10–12 hours saved per month)
Faster availability of validated energy insights for operations
Fewer reporting anomalies and less rework
ROI: Short-term: Positive due to reduced manual work
Long-term: High if expanded to additional buildings
Break-even: Within the first reporting year
Nordic Energy Data Quality Improvement – Phase 1
Scope/WBS and Delimitations
In Scope (3 simple tasks)
Extract meter data from 3 buildings
Clean & standardize the data
Produce a monthly energy summary report
Out of Scope
Automation
Real-time dashboards
Predictive analytics
Hardware upgrades
WBS
Data Extraction
Data Cleaning
Summary Reporting
Requirements:
Access to energy meter files for all 3 buildings
Support from IT Technician for data retrieval
Compliance with company data handling procedures
Results should support CO₂ reduction and internal sustainability goals
No special health or safety requirements
Status Report Date: 28 Nov 2025

## Slide 5: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Consequences:
If the project is not executed:
Monthly energy reporting will continue to rely on inconsistent and incomplete data.
CO₂ reduction and energy-saving initiatives will lack accurate baseline data.
Manual corrections will remain time-consuming and error-prone.
Future automation and dashboard development will be delayed.
Dependencies:
Access to meter data from Building A, B, and C.
IT support to retrieve and share the raw data files.
Energy Team availability to review the cleaned dataset.
Shared folder structure for storing consolidated data.
These dependencies are simple and minimal for this pilot phase.
Risks:
Missing or corrupted meter data for specific days.
Delays in obtaining files from IT or building operations.
Inconsistent data formats that require extra cleaning time.
Limited availability of the Data Analyst during key steps.
Risk exposure is low due to the small scope of the pilot.
Nordic Energy Data Quality Improvement – Phase 1
Strategic focus area(s):
<mark applicable by changing to Checkmark Bullet(s)>
1. We help our customer to reduce their CO2 footprint
2. We develop our electricity business to meet new demands
3. We build new business in flexibility services & integrated energy solutions
4. We develop IT into a strategic advantage
5. We engage our employees
Project Governance and Handover:
Project Portfolio Owner: Emma Lindström
Handover Partner: Lars Nyberg (Energy Operations Lead)
The cleaned dataset and monthly report will be handed over to the Energy Operations Team at project completion (expected 22–28 Nov 2025). They will use this data for monthly reporting and sustainability analyses.
Status Report Date: 28 Nov 2025

## Slide 6: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Acceptance to include Project in Project Portfolio:
Project Portfolio Owner PPO
Emma Lindström
<date>
Project Sponsor
Jonas Hallberg
<date>
Handover Partner
Lars Nyberg
<date>
Nordic Energy Data Quality Improvement – Phase 1
Status Report Date: 28 Nov 2025

## Slide 7: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Tender outcome:
No external tendering process was required for this pilot phase. All activities will be performed using internal resources from NordicTech Solutions AB, including data extraction, cleaning, and reporting. No external vendors, software purchases, or contracts were involved.
Implementation plan:
A simple 4-week implementation plan, aligned with the 3 tasks:
Week 1 — Data Extraction (Completed)
📅 1–7 Nov 2025
IT Technician retrieves meter data from all 3 buildings
Files validated and stored in shared workspace
Week 2–3 — Data Cleaning (In Progress)
📅 8–21 Nov 2025
Combine and standardize the datasets
Remove duplicates, fill gaps, validate consumption values
Review with Energy Team
Week 4 — Summary Report Preparation (Not Started)
📅 22–28 Nov 2025
Create monthly usage report
Prepare clean dataset handover package
Final review and closure meeting
Internal stakeholders: Project Manager, Data Analyst, IT Technician, Energy Team
External stakeholders: None for this pilot project
Nordic Energy Data Quality Improvement – Phase 1
Contract, SLA and Payments
As this is an internal pilot project, no external contract or SLA is required. All work is executed under existing internal agreements and standard working procedures.
Payment Terms:
Total estimated cost: 75,000 SEK (internal labor only)
No external supplier costs
No invoices or payment schedules needed
Scope and Quality:
Deliverables: Clean dataset + monthly summary report
Quality criteria: 95% validated and complete data
Testing: Manual validation by Energy Team
Status Report Date: 28 Nov 2025

## Slide 8: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Acceptance of Contract, SLA and Payment Terms:
Project Portfolio Owner PPO
Emma Lindström
Approved on: 1 Nov 2025
Project Sponsor
Jonas Hallberg
Approved on: 2 Nov 2025
Handover Partner
Lars Nyberg
Approved on: 2 Nov 2025
Nordic Energy Data Quality Improvement – Phase 1
Status Report Date: 28 Nov 2025

## Slide 9: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Risk Management:
Nordic Energy Data Quality Improvement – Phase 1
Status Report Date: 28 Nov 2025

## Slide 10: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Project Organization:
Organizational structure for the TG3 pilot project (Nov 2025)
Nordic Energy Data Quality Improvement – Phase 1
Sponsor
Jonas Hallberg
Project Member
Sara Holm
Project Manager
Maria Svensson
IT Project Manager
Daniel Larsson
Project Member (Data Analyst)
Anna Karlsson
Project Member
Mikael Jonsson
Project Member (Energy Operations Rep)
Lars Nyberg
Project Member (IT Support Technician)
Erik Johansson
Steering Group
Elin Bergström
Status Report Date: 28 Nov 2025

## Slide 11: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Work Breakdown Structure - WBS:
Nordic Energy Data Quality Improvement – Phase 1
Scope
Area 1: Data Extraction
Area 2: Data Cleaning & Standardization
Area 3: Repoirting & Handover
WP1.1 – Retrieve meter data from Building A
WP1.2 – Retrieve meter data from Building B
WP2.1 – Combine datasets into a unified format
WP2.2 – Remove duplicates and fill misssing values
WP3.1 – Create monthly energy summary report
WP3.2 – Prepare clean dataset package
WP1.3 – Retrieve meter data from Building C
WP2.3 – Validate consumption values with Energy Team
WP3.3 – Handover to Energy Operations Team
Status Report Date: 28 Nov 2025
Timeline:
WP1.x tasks take place in Week 1 (1–7 Nov)
WP2.x tasks take place in Weeks 2–3 (8–21 Nov)
WP3.x tasks take place in Week 4 (22–28 Nov)

## Slide 12: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Network Diagram
Nordic Energy Data Quality Improvement – Phase 1
Start
WP1.1 – Retrieve meter data from Building A
WP1.2 – Retrieve meter data from Building B
WP1.3 – Retrieve meter data from C
WP2.1 – Combine datasets into unified format
WP2.2 – Clean missing/duplicate values
WP2.3 – Validate cleaned data with Energy Team
WP3.1 - Create monthly energy summary report
WP3.2 - Prepare clean dataset package
WP3.3 – Handover to Energy Operations
Stop
Status Report Date: 28 Nov 2025
Timeline:
WP1.x tasks take place in Week 1 (1–7 Nov)
WP2.x tasks take place in Weeks 2–3 (8–21 Nov)
WP3.x tasks take place in Week 4 (22–28 Nov)

## Slide 13: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Activity List:
Nordic Energy Data Quality Improvement – Phase 1
Status Report Date: 28 Nov 2025

## Slide 14: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Gantt Chart:
Nordic Energy Data Quality Improvement – Phase 1
Activity | Week 1 (Nov 1–7) | Week 2 (Nov 8–14) | Week 3 (Nov 15–21) | Week 4 (Jun 22–28)
Data Extraction | (7 Days) |  |  | 
Data Cleaning & Standardization |  | (7 Days) | (7 Days) | 
Reporting & Handover |  |  |  | (7 Days)
Status Report Date: 28 Nov 2025

## Slide 15: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
SWOT Analysis:
Nordic Energy Data Quality Improvement – Phase 1
STRENGTHS (Internal, Helpful)
Clear and limited projects scope (only 3 tasks)
Uses internal resource only – no external dependencies
Fast implementation (4 weeks total)
Strong support from Energy Operations Team
Improves data reliability immediately
WEAKNESSES (Internal, Harmful)
Manual data cleaning required
Small project team may have competing priorities
Depends on timely input from IT Technician and Energy Team
Limited to 3 pilot buildings (not full company portfolio)
OPPORTUNITIES (External, Helpful)
Can extend to real-time monitoring dashboards in future phases
Supports CO2 reduction and sustainability reporting needs
Enables data-driven energy savings across more buildings
Potential to automate cleaning and reporting in future phases
Creates foundation for smarter energy analytics
THREATS (External, Harmful)
Delays from building operations or IT access issues
Future meter hardware upgrades may change data formats
Unexpected data quality issues may increase workload
Other corporate priorities may limit resource availability
HELPFUL
HARMFUL
EXTERNAL
INTERNAL
Status Report Date: 28 Nov 2025
SWOT Analysis:

## Slide 16: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Stakeholder mapping:
Nordic Energy Data Quality Improvement – Phase 1
Status Report Date: 28 Nov 2025

## Slide 17: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Communication Plan:
Nordic Energy Data Quality Improvement – Phase 1
Status Report Date: 28 Nov 2025

## Slide 18: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Handover Management:
The Project Manager hands over the cleaned dataset and summary report to the Handover Manager in the Operating Unit once TG4 is approved. The Handover Manager is responsible for ensuring that the Energy Operations team receives all updated documentation and that the data is ready for ongoing monthly reporting.
The Operating Unit Manager must ensure resources are available for the transition and appoint a Super User who will support daily operations after the project ends. The Super User will act as the local contact for any questions regarding the cleaned dataset and reporting process.
The Sponsor approves the final delivery and ensures that expected benefits (improved data quality, smoother reporting, reduced manual corrections) are realized over time.
Nordic Energy Data Quality Improvement – Phase 1
Project Organization
Operating Unit
Maintenance
Handover Manager
Super User
Sponsor
[Jonas Hallberg]
Project Manager
Maria Svensson
IT Project Manager
Daniel Larsson]
Project Member (Energy Ops)
Lars Nyberg
Project Member
(Data Analyst)
Anna Karlsson
Steering Group
Eva Lundström
Project Member (IT Technician)
Erik Johansson
Manager
Henrik Olofsson
Sofia Bergström
Johan Wiklund
Status Report Date: 28 Nov 2025

## Slide 19: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Lessons Learned:
Nordic Energy Data Quality Improvement – Phase 1
Status Report Date: 28 Nov 2025

## Slide 20: TG3 Project Plan + Establishment Project Period: 1 Nov 2025 – 28 Nov 2025
Rest Activities:
Nordic Energy Data Quality Improvement – Phase 1
Status Report Date: 28 Nov 2025

## Slide 21: TG3 Project Plan + Establishment
Financial Performance
Nordic Energy Data Quality Improvement – Phase 1
Benefits / Value (Financial + Operational)
Value Delivered
Reduced manual data cleaning time by ~12 hours/month
Improved data quality → fewer reporting errors
Potential long-term savings through automation
Faster monthly reporting process
.
ROI Snapshot
ROI Assessment
Short-term ROI: Moderate, due to small pilot scope
Long-term ROI: High, if extended to more buildings and
Break-even: Achievable within the first full reporting cycle if scaled
Status Report Date: 28 Nov 2025